## Risks
Risk Assessment Template
Organisation: Citrenz Group
Initiative, Project, and/or Engagement: Web conference for citrenz
Author: Ryan Wassell
Date: 8/03/2026
|  |  | Pre-Mitigation Risk |  |  |  | Post-Mitigation Risk
| Risk Statement |  | (Scale) | (Scale) |  |  | (Scale) | (Scale)
# | Condition | Consequence | Probability | Impact | Exposure | Mitigation | Probability | Impact | Exposure | Contingency | Triggers
1 | Sickness | Could miss out on client meetings, miss important information in class, lose time to work on project | 35% | 8 | 2.8 | Get enough sleep, stay hydrated, practice good hygiene | 25% | 5 | 1.25 | Work from home, email client/teachers | Being around other sick people, stress, poor diet, lack of sleep
2 | Scope Creep | Miss out on deadlines due to adding more features | 15% | 5 | 0.75 | Regularly talk to client | 5% | 2 | 0.1 | Do must have features first | Not sticking to project requirements, adding new features before must haves are finished
3 | Poor Time Management | Rushed work, handing in work late | 50% | 7 | 3.5 | Stick to a timeline, try and do a little bit everyday | 25% | 5 | 1.25 | Ask for an extension | Procrastination, multiple projects
4 | Data loss/corruption | Lost project progress | 10% | 10 | 1 | Back ups, Uploading to github | 5% | 5 | 0.25 | Restore from backups/github, ask for extra time if backsups/github doesn’t work | Software/Hardware Issues
5 | Lack of specific technical logic for project | Poor quality work, missing out on deadlines | 30% | 8 | 2.4 | Ask for help, search online resources | 20% | 5 | 1 | Ask for help, allocate extra time to learn content | New concepts needed for project
6 |  |  |  |  | 0 |  | 0 | 0 | 0
7 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
8 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
9 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
10 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
11 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
12 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
13 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
14 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
15 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
16 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
17 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
18 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
19 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
20 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0
Note on D8: Articulate the scale being used for probability inside of the parenthesis. E.g. (1-100%) Note: 100% would mean the item is no longer a risk and has become a problem.
Note on E8: Articulate the scale being used for impact inside the parenthesis. E.g. (1-10). Note: scale must have the same range as the probability.
Note on H8: Articulate the scale being used for probability inside of the parenthesis. E.g. (1-100%) Note: 100% would mean the item is no longer a risk and has become a problem.
Note on I8: Articulate the scale being used for impact inside the parenthesis. E.g. (1-10). Note: scale must have the same range as the probability.
Note on A9: Use this column as the risk identifier which, allows each risk to be uniquely identified.
Note on B9: Use this column to capture the "likely cause" of the risk. Be detailed enough so that you can start forming mitigation plans.
Note on C9: Use this column to capture the result of the risk, should it happen. If the consequences cannot be mitigated, you will have to dealt with them in a contingency plan.
Note on D9: Use this column to estimate the probability the risk will occur. Suggest using a percentage-based scale (1-99%).
Note on E9: Use this column to estimate the amount of impact or severity of the risk.
Note on F9: This column is computed as probability x impact. Once all risks have been entered, sort by this column to identify your biggest risks.
Note on G9: Use this column to document what plans the team has to prevent the risk or to reduce the impact before occurance. This may require creating a separate, more detailed plan.
Note on H9: Use this column to estimate the probability the risk will occur. Suggest using a percentage-based scale (1-99%).
Note on I9: Use this column to estimate the amount of impact or severity of the risk.
Note on J9: This column is computed as probability x impact. Once all risks have been entered, sort by this column to identify your biggest risks.
Note on K9: Use this column to identify what will need to be done if the risk becomes reality. This may require creating a separate, more detailed plan.
Note on L9: Use this column to identify what would prompt you to execute the contingency plan. A trigger is usually a date or some sort of threshold.